MASTER RESEARCH AGREEMENT

Between

TEXAS A&M TRANSPORTATION INSTITUTE

And

FORT BEND COUNTY

WORK AUTHORIZATION NO. 5

AMENDMENT NO. 1

This Amendment (the “Amendment”) is entered into by and between Fort Bend County, a political subdivision of the State of Texas (hereinafter referred to as "County"), and the Texas A&M Transportation Institute, a member of The Texas A&M University System (“System”) and an agency of the State of Texas, having its principal place of business at 400 Harvey Mitchell Parkway South, Suite 300, College Station, Texas 77845 (hereinafter referred to as "TTI").

WHEREAS, County and TTI entered into a Master Research Agreement (the “Agreement”) effective as of March 8, 2016, whereby except as otherwise specified herein, the terms and conditions of that Agreement are incorporated by reference into this Work Authorization; and

THAT, WHEREAS, County and TTI also accepted and executed Work Authorization No. 5 (the “Work Authorization”) to the Agreement on February 6, 2018; and

NOW, THEREFORE, the Parties hereto agree to amend Work Authorization No. 5 by extending the period of performance from April 30, 2018 to May 31, 2018.  The revised Work Authorization No. 5 shall read as follows:

- Period of Performance.  The research shall be conducted during the period February 1, 2018 through May 31, 2018 and will be subject to extension only by mutual written agreement of both parties.

- Reports.  TTI shall submit the following reports to FBC:

| Report |  | Due Date |
| --- | --- | --- |
| D1 | Summary Document of Task 1 Findings | March 31, 2018 |
| D2 | Training Coursebook | April 30, 2018 |
| D3 | Training Powerpoint Presentation | May 31, 2018 |

Except as provided herein, all other terms and conditions of the Agreement and Work Authorization shall remain unchanged.

IN WITNESS WHEREOF, the parties have caused this Amendment No. 1 to Work Authorization No. 5 to be executed by their authorized representative.

TEXAS A&M TRANSPORTATION			FORT BEND COUNTY

INSTITUTE

By:  							By:

Title: 	Agency Director				Title: County Judge

Date:  	April 16, 2018					Date: