## 3-03
PROJECT BUDGET ESTIMATE | [8 empty] | INSTRUCTIONS INCLUDED IN THIS COLUMN
FORT BEND COUNTY MOBILITY 2020
PROJECT NO: |  | 3-12 |  |  |  | COST SUMMARY |  |  | Preliminary Mobility Precinct - Project number with dash
ROAD: |  | Pink Oak Road |  |  |  | ENGINEERING |  | 34000
LIMITS: | FROM: | At Katy Flewellen Road |  |  |  | RIGHT OF WAY & UTILITIES |  | 0
| TO: |  |  |  |  | CONST. PHASE SERVICES |  | 13800
LENGTH: | FEET = | 210 |  |  |  | CONSTRUCTION |  | 173500
| STA = | 2.1 |  |  |  | TOTAL PROJECT BUDGET |  | 221300
| MILES = | 0.04 |  |  |  | COUNTY BOND AMOUNT |  | 230000
SHORT DESCRIPTION: |  |  | Add SB right-turn lane. | [5 empty] | Provide description for program summary
DESCRIPTION: |  | Design and construct southbound dedicated right-turn lane. | [6 empty] | Provide detailed project description, including unusual cost information.
[6 empty] | PREPARED BY: | Schaumburg & Polk, Inc.
[6 empty] | REVISION DATE: | 2020-07-02
DESCRIPTION |  |  |  | UNIT | QTY | COST | AMOUNT | COMMENTS/
ASSUMPTIONS
ROADWAY & DRAINAGE
| REMOVAL/PREP ROW |  |  | STA | 2.1 | 8000 | 16800 |  | Insert Description (Revise COST to reflect conditions)
| CONCRETE PAVEMENT | [7 empty] | Paving items include subgrade, base, pavement and earthwork
|  | 2-LANE C&G (27' F-F) |  | STA |  | 22000 | 0 |  | Insert Description
|  | 3-LANE C&G (40' F-F) |  | STA |  | 28000 | 0
|  | 4-LANE DIVIDED C&G (2-24' F-F) |  | STA |  | 40000 | 0 |  | Insert Description (USE 1/2 STA FOR HALF BOULEVARD)
|  | 6-LANE DIVIDED C&G (2-36' F-F) |  | STA |  | 54000 | 0 |  | Insert Description
|  | ADDITIONAL LANE |  | STA | 2.1 | 12000 | 25200 | Right-turn lane | Assume 12-foot wide with saw cut and removal of existing curb.
|  | TRAFFIC ROUNDABOUT |  | EACH |  | 60000 | 0 |  | 2-lane maximum with median treatment and intersection lighting
ASPHALT PAVEMENT
|  | 12' WIDE LANE |  | STA |  | 12000 | 0
|  | 6' WIDE SHOULDER |  | STA |  | 8500 | 0 |  | Insert Description
|  | 24' REHABILITATION / OVERLAY |  | STA |  | 10000 | 0 |  | Insert Description
| STORM SEWER SYSTEM |  |  | STA |  | 20000 | 0 |  | Insert Description (Revise COST for open ditch & special conditions)
| CROSS CULVERT |  |  | EA |  | 25000 | 0 |  | Insert Description (Revise COST for open ditch & special conditions)
| OUTFALL |  |  | EA |  | 25000 |  |  | Insert Description (Revise COST for open ditch & special conditions)
| INLET ADJUSTMENT |  |  | EA | 1 | 8000 | 8000 |  | Other items as necessary per project or erase text, but leave cells
| OTHER |  |  | EA |  | 1 | 0 |  | Other items as necessary per project or erase text, but leave cells
| OTHER |  |  | EA |  | 1 | 0 |  | Other items as necessary per project or erase text, but leave cells
SUBTOTAL ROADWAY & DRAINAGE | [6 empty] | 50000
UTILITIES | [8 empty] | Potential conflict with exist utilities
| RELOCATE WATER DISTRIBUTION |  |  | STA |  | 1500 | 0 |  | Insert Description
| RELOCATE WATER TRANSMISSION |  |  | STA |  | 3500 | 0 |  | Insert Description
| RELOCATE SANITARY SEWER |  |  | STA |  | 6500 | 0 |  | Insert Description
| RELOCATE FORCE MAIN |  |  | STA |  | 6500 | 0 |  | Insert Description
SUBTOTAL UTILITIES | [6 empty] | 0
DESCRIPTION |  |  |  | UNIT | QTY | COST | AMOUNT | COMMENTS/
ASSUMPTIONS
MISCELLANEOUS
| SIGNALIZED INTERSECTION |  |  | EA | 0.25 | 200000 | 50000 | Traffic signal pole relocation | Insert Description
| SIGNING & PAVEMENT MARKINGS |  |  | STA | 2.1 | 1200 | 2520 | Unit cost adjusted for intersection work | Insert Description
| BLOCK SOD & SEEDING |  |  | STA | 2.1 | 1000 | 2100 |  | Insert Description
| SWPPP |  |  | STA | 2.1 | 2000 | 4200 |  | Insert Description
SUBTOTAL MISCELLANEOUS | [6 empty] | 58820
OTHER ITEMS
| SIDEWALK (One side @ 5-foot wide) |  |  | STA |  | 4000 | 0 | No sidewalks | Insert Description
| DETENTION POND |  |  | AC-FT |  | 50000 | 0 |  | Insert Description
| BRIDGE |  |  | SF |  | 120 | 0 |  | Insert Description
| RETAINING WALL |  |  | SF |  | 75 | 0 |  | Insert Description
| PUMP STATION |  |  | EA |  | 50000 | 0 |  | Insert Description
| IN-LINE DETENTION |  |  | AC-FT |  | 300000 | 0 |  | Insert Description
| CURB RAMP |  |  | EA | 4 | 2500 | 10000 |  | Other items as necessary per project or erase text, but leave cells
| OTHER |  |  | EA |  | 1 | 0 |  | Other items as necessary per project or erase text, but leave cells
| OTHER |  |  | EA |  | 1 | 0 |  | Other items as necessary per project or erase text, but leave cells
| OTHER |  |  | EA |  | 1 | 0 |  | Other items as necessary per project or erase text, but leave cells
Other items as necessary per project or erase text, but leave cells
SUBTOTAL OTHER ITEMS | [6 empty] | 10000
SUBTOTAL CONSTRUCTION COST | [6 empty] | 118820
TRAFFIC CONTROL PLAN (2%-8% x CONST ITEMS) |  |  |  | BUDGET |  | 9% | 10700 | Temporary signalization | Set % and provide explanation
MOBILIZATION (% x CONST ITEMS) |  |  |  | BUDGET |  | 3% | 3600
CONTINGENCY (% x CONST ITEMS) |  |  |  | BUDGET |  | 25% | 29700
PROGRAM & ESCALATION (% x CONST ITEMS) |  |  |  | BUDGET |  | 9% | 10700
CONSTRUCTION COST TOTAL | [6 empty] | 173520
DESCRIPTION |  |  |  | UNIT | QTY | COST | AMOUNT | COMMENTS/
ASSUMPTIONS
ENGINEERING & DESIGN
| ENVIRONMENTAL REVIEW (Desktop Only) |  |  | BUDGET |  | 8000 | 8000 |  | Add detailed Wetlands Study & Mitigation below
| GEOTECH ENGINEERING (% x CONST COST) |  |  | BUDGET |  |  | 0
| PREL ENG REPORT (% x CONST COST) |  |  | BUDGET |  | 6% | 10400 | Includes Survey
| PS&E DOCUMENTS (% x CONST COST) |  |  | BUDGET |  | 9% | 15600
SUBTOTAL ENGINEERING | [6 empty] | 34000
CONSTRUCTION PHASE SERVICES
| CONST MANAGEMENT (% x CONST) |  |  | BUDGET |  | 4% | 6900
| LABORATORY TESTING (% x CONST) |  |  | BUDGET |  | 4% | 6900
SUBTOTAL CONSTRUCTION PHASE SERVICES | [6 empty] | 13800
RIGHT OF WAY & UTILITIES
| UNDEVELOPED |  |  | SF |  | 12 | 0 | No proposed ROW needed | Include max-min amount for full range of the project
| HARD CORNERS |  |  | EA |  | 5000 | 0 |  | Insert Description
| STRUCTURES |  |  | EA |  | 60000 | 0 |  | Insert Description
| ROW APPRAISAL & ACQUISITION COSTS |  |  | PARCEL |  | 4000 | 0 |  | Insert Description
| PIPELINE RELOCATION ( <8" ) |  |  | EA |  | 300000 | 0 | No pipelines | <8"=$300,000; 8"-16"=$600,000 & >16"=$800,000 or best available info
| PIPELINE RELOCATION ( 8"-16" ) |  |  | EA |  | 600000 | 0 | No pipelines | <8"=$300,000; 8"-16"=$600,000 & >16"=$800,000 or best available info
| PIPELINE RELOCATION ( >16" ) |  |  | EA |  | 800000 | 0 | No pipelines | <8"=$300,000; 8"-16"=$600,000 & >16"=$800,000 or best available info
| ENVIRONMENTAL MITIGATION |  |  | BUDGET |  | 1 | 0 | Environmental Services + Mitigation | Include identified locations requiring mitigation.
| OTHER UTILITIES |  |  | BUDGET |  | 1 | 0 |  | Utilities (other than pipelines) adjoining ROW in easements
SUBTOTAL RIGHT OF WAY | [6 empty] | 0
PROJECT COST SUMMARY
| ENGINEERING | [5 empty] | 34000 |  | Rounded to nearest $100's
| RIGHT OF WAY | [5 empty] | 0 |  | Rounded to nearest $100's
| CONSTRUCTION PHASE SERVICES | [5 empty] | 13800 |  | Rounded to nearest $100's
| CONSTRUCTION | [5 empty] | 173500 |  | Rounded to nearest $100's
TOTAL PROJECT COST | [6 empty] | 221300 |  | Rounded to nearest $100's
PROJECT BUDGET & RESOURCES | [6 empty] | PROJECT TOTAL
PROJECT COST SUMMARY
| ENGINEERING |  |  |  |  | 34000
| RIGHT OF WAY & UTILITIES |  |  |  |  | 0
| CONSTRUCTION PHASE SERVICES |  |  |  |  | 13800
| CONSTRUCTION |  |  |  |  | 173500
TOTAL PROJECT BUDGET : | [6 empty] | 221300
OTHER PROJECT RESOURCES
CONTRIBUTION FROM: |  |  | NONE | [5 empty] | City, Other Agency or NONE
| CATEGORY |  |  | LOCAL SHARE |  | LOCAL AMOUNT
| ENGINEERING |  |  |  |  | 0 |  |  | Insert Description
| RIGHT OF WAY & UTILITIES |  |  | 87.8% |  | 0 |  |  | Insert Description
| CONSTRUCTION PHASE SERVICES |  |  |  |  | 0 |  |  | Insert Description
| CONSTRUCTION |  |  |  |  | 0 |  |  | Insert Description
| OTHER |  |  |  |  | 0 |  |  | Other items as necessary per project or erase text, but leave cells
| OTHER |  |  |  |  | 0 |  |  | Other items as necessary per project or erase text, but leave cells
| OTHER |  |  |  |  | 0 |  |  | Other items as necessary per project or erase text, but leave cells
| OTHER |  |  |  |  | 0 |  |  | Other items as necessary per project or erase text, but leave cells
TOTAL OTHER CONTRIBUTIONS | [6 empty] | 0
COUNTY BOND AMOUNT | [6 empty] | 230000 |  | Rounded up to increment of $100k